## Sheet1
ACTION PLAN FOR THE IMPLEMENTATION OF THE NATIONAL STRATEGY FOR THE MANAGEMENT AND CONTROL OF DOGS WITH AND WITHOUT OWNERS 2023-2025
Strategic objectives:
1. DEVELOPING A SUITABLE ENVIRONMENT FOR DPM
Specific Objectives | Activities | Indicator | Sources of financing | Budget |  |  | Responsible and supporting institutions | Deadline | Output
|  |  |  | 2023 | 2024 | 2025
1.1 Establishment of the task force at the central, local/inter-municipal level | 1.1.1 Notification of relevant stakeholders for the establishment of the task force | At least four (4) regular meetings within the year to be held | The budget of the Republic of Kosovo | 2000 | 2000.5 | 2001 | Responsible institution: MLGA Supporting institutions: MAFRD FVA MIA CSO | Q1 - Q4 2023 | Task force established at central and local level, as needed
| 1.1.2 Drafting the terms of reference for the task force. | Approval of terms of reference | [5 empty] | Q1 2023 | Drafting and approval of terms of reference by group members
| 1.1.3. Drafting of periodic reports for CMP | Two reports within a year | [5 empty] | Q2-Q4 | Finalization of CMP reports
1.2. Drafting of the MDCP based on the national strategy for the management and control of dogs with and without owners | 1.2.1. Study/evaluation of dog dynamics at the municipal level | Study/survey reports on the number and dynamics of dogs with and without owners. | Donors - CSO | 20000 | 20000 | 20000 | Responsible institution: Municipalities Supporting institutions: MAFRD FVA MIA CSO | Q1 - Q2 2023 | Reports on the dynamics and number of dogs at the municipal level
| 1.2.2. Drafting of local programs | Designing a model program for all municipalities | The budget of the Republic of Kosovo | 100 | 100 | 100 | Responsible institutions: MLGA, AKM, Task Force, Municipalities Supporting institutions: MAFRD FVA | Q2 | Model program designed
| 1.2.3. Organization of workshops for the presentation of the MDCP model | Organizing five (5) regional workshops |  | 10000 | 10000 | 10000 |  |  | Five (5) regional workshops organized with municipalities
| 1.2.4.Monitoring and evaluation of CMP interventions | Drafting the annual report |  | 200 | 200 | 200 |  |  | Annual report drafted
1.3 Building local capacities | 1.3.1. Training needs assessment and gap analysis. | Identification of technical deficiencies and professional knowledge | State funding. Other resources: External funding, EU projects and other donations | 10000 | 10000 | 10000 | Responsible institution: FVA Supporting institutions: Veterianry Faculty Working Group Veterinary Chamber | Q1 -Q4 | Organizing five (5) trainings
2. DEVELOPMENT OF A COMPREHENSIVE LEGAL FRAMEWORK FOR DPM
Specific Objectives | Activities | Indicator | Sources of financing | Budget |  |  | Responsible institutions | Deadline | Output
|  |  |  | 2023 | 2024 | 2025
2.1 Advancement of the legislative framework for the care of animals | 2.1.1. Expost evaluation of Law No. 02/L-10 on Animal Welfare | Expost evaluation analysis of the law | State funding | 1000 | 1000.5 | 1001 | Responsible institution: MAFRD Supporting institutions: FVA | Q1-Q4 | Drafted report
| 2.1.2. Review of legislation in force | Identification of legislative priorities | State funding. Other resources: Projects from EU funds. | 1000 | 1000.5 | 1001 | Responsible insitution: MAFRD Supporting institutions: FVA IRK | Q1-K4 | Ordering of legal and sub-legal acts, revised
2.2 Identification and registration of accompanied animals | 2.2.1 18,700 microchips were provided for dogs with owners | Distribution of microchips to private veterinarians | Funding by BRK, EC | 140250 |  |  | Leading: FVA | Q3 2022 - Q3 2023 | Application of microchips and data reporting in the FVA database
| 2.2.2 Conclusion of contracts with veterinary entities for I&R of accompanied animals. | Number of contracted veterinarians |  | 220000 |  |  |  | Q3 2022
| 2.2.3 200 microchip readers have been provided and a database has been created. | Data on identified animals were recorded |  | 20000 |  |  |  | Q3 2022 and ongoing | Animal identification and registration is functional. The database is updated continuously
2.3 Control of breeders of accompanied animals for keeping and sale | 2.3.1 Establishing policies for breeders of accompanied animals for keeping and sale | Drafting of AI for breeders of accompanied animals for keeping and sale; Organizing two (2) workshops with relevant stakeholders | State funding. Other resources: Projects from EU funds. | 3000 |  |  | Responsible insitution: MAFRD Supporting insitutions: FVA MLGA KVC CSO | Q1 -Q4 2023 | Approval of AI
| 2.3.2 Establishing policies for keeping dangerous dogs | Drafting of municipal regulations for the movement of dogs in public spaces |  |  | 3000 |  | Responsible institution: MAFRD Supporting institutions: FVA MLGA KVC CSO | Q1 - Q4 2024 | Approval of regulation
2.4 Control of international movements of dogs | 2.4.1 Border control to combat illegal trade. | Identified and registered commercial imports | State funding. Other resources: Projects from EU funds, owners of dogs. | 1000 | 1000.5 | 1001 | Responsible insitution: FVA Supporting insitutions: MIA Customs | Q2 ongoing | Periodic reports on border control to combat illegal trade, drawn up
3. GENERAL SOCIAL EDUCATION AND PROMOTION OF RESPONSIBLE OWNERSHIP
Specific Objectives | Activities | Indicator | Sources of financing | Budget |  |  | Responsible institutions | Deadline | Output
|  |  |  | 2023 | 2024 | 2025
3.1 Development of information campaigns
| 3.1.2 Organization of information campaigns in seven (7) regions regarding public awareness about behavior towards dogs | Number of media and social networks campaigns Number of campaigns in the community | State budget Other sources: Projects from EU funds, international CSOs and organizations, donations. | 120000 | 120000 | 120000 | Responsible insitutions: FVA MAFRD MEST Supporting insitutions: MLGA AKM KUNICIPALITIES IN (International Organizations) CSOs. | Q1 - Q4 | Organization of information campaigns in seven (7) regions, organized
| 3.1.3 Organizing activities and workshops in primary and secondary schools on animal welfare and responsible pet ownership | Number of campaigns in schools Number of media and social networks campaigns
4. CONTROL OF REPRODUCTION OF DOGS WITH AND WITHOUT OWNER AND PROVISIONS OF VETERINARY CARE
Specific Objectives | Activities | Indicator | Sources of financing | Budget |  |  | Responsible institutions | Deadline | Output
|  |  |  | 2023 | 2024 | 2025
4.1. Inspektimi veterinar | 4.1.1. Building veterinary inspection capacities | Number of inspectors employed |  | 180000 | 90045 | 90090.02 | Responsible insitution: FVA | Q1 - Q2 2023 | Recruitment of twelve (12) veterinary inspectors and purchase of six (6) official cars
4.2 Support in the treatment of dogs | 4.2.1 Development of campaigns to support castration/sterilization of dogs with owners | Number of media and social networks campaigns Number of campaigns in the community | State budget Other sources: Projects from EU funds and donations, dogs' owners | 1500000 | 1000000 | 1000000 | Responsible insitution: Municipalities Supporting insitutions: FVA Veterinary Chamber, Private veterinarians, CSOs. | Q4 2022 - Q4 2023 | Prevention of dog breeding
| 4.2.2 Continuous training and support in the development of the latest surgical skills and techniques for veterinarians | Number of trainings
| 4.2.3. Treatment of dogs in emergency cases | Treatment of injured or sick dogs where euthanasia is not required but recovery.
| 4.2.4. Catch, neuter, vaccinate, release | Number of treated dogs
| 4.2.5. Euthanasia of sick and aggressive dogs | Number of dogs euthanized
4.3 Prevention of infectious - zoonotic diseases | 4.3.1 Vaccination of dogs against Rabies and parasitic diseases | Number of dogs vaccinated and treated for parasites | State budget Other sources: Projects from EU funds, | 200000 | 200000 | 200000 | Responsible insitution: FVA Veterinary Chamber Municipalities Supporting insitutions: MAFRD NIPHK (National Institute of Public Health of Kosovo) |  | All dogs vaccinated against rabies and parasitic diseases
5. DEVELOPMENT OF LOCAL DOG POPULATION MANAGEMENT SERVICES
Specific Objectives | Activities | Indicator | Sources of financing | Budget |  |  | Responsible institutions | Deadline | Output
|  |  |  | 2023 | 2024 | 2025
5.1 Municipal Capacity building development plans for dog population control | 5.1.1 Realization and evaluation of the skills and capacities necessary for the implementation of the MPDP at the municipal level. | Preparation of draft local plans | Other sources: OSCE, donations from National and International CSOa, EU funds. | 2500 |  |  | Responsible institutions: MLGA, FVA, AKM, MAFRD Supporting insitutions: Faculty of Agriculture and Veterinary Veterinary Chamber | Q1 2023 | Municipal Plans approved
38 municipalities have prepared local draft plans
5.2 Building physical capacities for the shelters of accompanied animals | 5.2.1 Needs Assessment for the establishment of shelters of accompanied animals | Establishment of shelters for accompanied animals | State funding Other sources: EU funds, International CSOs and donations. | 2000000 |  |  | Responsible instituion: Municipalities Supporting institutions: MLGA FVA MAFRD Veterinary Chamber, CSOs, Municipal committees. | Q1 - Q2 2023 | Evaluation report
5.3 Handling of environmental issues in all phases of strategy implementation | 5.3.1 Allocation of local areas for burying animal remains. | Disposal of mortal remains | State funding. | 200000 | 200000 | 100000 | Responsible institution: Municipalities Supporting institutions: FVA MESPI | Q1 2023 - Q4 2025 | Environment Protection
5.4. Feeding of stray dogs in municipalities | 5.4.1.Setting places as feeding points for stray dogs | Setting up feeding points and food for stray dogs | Funding from the state | 600000 | 600000 | 500000 | Responsible institution: Municipalities | Q1-Q4 | Annual report drafted
5.5 Control of dog movements in public spaces | 5.5.1 Development of specific municipal rules that determine the way dogs are kept in cities and the movement of dogs in public spaces | Drafting of municipal regulations on the movement of dogs in public spaces | State funding Other sources: Municipal Authorities, EU funding, donations, corporate financing, OSCE | 1500 | 1500 | 1500 | Responsible institutions: Municipalities, MLGA, MAFRD, FVA Supporting institutions: AKM Faculty of Agriculture and Veterinary Veterinary Chamber | Q1 2023- Q4 2025 | Management and control of the movement of dogs with owners
| 5.5.2 Citizens to be informed about the established rules | Information leaflets and visible materials in public spaces |  | 100000 | 100000 | 100000 | Responsible institution: Municipalities Supporting institutions: MLGA CSOs, citizen groups. | Q1 2023 and ongoing
|  |  |  | 5332550 | 2359847 | 2156894.02
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kjo pikë e shtuar është në përshtatje të Strategjisë për të anketuar/studiuar numrin e qenve në rrugë dhe dinamikën e tyre për të dizajnuar masat e përshtatshme dhe të nevojshme për secilën komunë apo rajon (të përbërë nga disa komuna). Ky koment ndërlidhet me komentin tek indikatori i pikës 1.2.2. t
Note on A48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pika 7.6.4 e Strategjise, parasheh menaxhimin e qasjes ne burime te ushqimit te qenve endacak. Deri ne strehimin e qenve, patjeter qe duhet nje plan se si te veprohet ne rruge dhe me mbeturinat qe terhekin qente endacak. Sipas udhezimeve te ICAM dhe strategjise tone, kjo mund te behet duke i “drejtuar” qente kah nje vend me adekuat per ta ku edhe mund te ushqehen.